## Task List
High Level | Tasks | Time Allotment (hrs; no margin) | Time Allotment (hrs; conservative) | Fall 2018? | Status | Assumptions
Mechanical Design | Design storage compartment | 4 | 8 | Y | Not started | Time Uncertainty Multiplier | 2
| Design wheel base | 7 | 14 | Y | Not started | Weekly Time Allotment (hrs) | 10
| Design sensor mounting | 4 | 8 | Y | Not started
| Select/design power transmission mechanics | 8 | 16 | Y | Not started |  | Weeks to Completion
| Design controls/power systems enclosure | 8 | 16 | Y | Not started | No margin; all tasks | 26.4
Analysis | Analyze payload capacity | 2 | 4 | Y | Not started | Conservative; all tasks | 52.8
| Analyze electrical load requirements | 3 | 6 | Y | Not started | No margin; select tasks | 9.9
| Analyze mechanical power/torque distribution | 2 | 4 | Y | Not started | Conservative; select tasks | 19.8
Part Selection | Select motors | 1 | 2 | Y | Not started
| Select electrical hardware (power supplies/circuit elements) | 5 | 10 | Y | Not started
| Select sensors for obstacle detection | 1 | 2 | Y | Not started
| Select sensors for target tracking | 5 | 10 |  | Not started
Prototyping | Build storage compartment prototype | 5 | 10 | Y | Not started
| Build wheel base prototype | 3 | 6 | Y | Not started
| Build sensor mounting | 5 | 10 | Y | Not started
| Build controls/power systems enclosure | 5 | 10 | Y | Not started
| System integration and assembly | 8 | 16 | Y | Not started
Controls | Configure circuit with necessary elements | 2 | 4 | Y | Not started
| Check functionality of each sensor independently | 8 | 16 | Y | Not started
| Program basic motor control | 2 | 4 | Y | Not started
| Program obstacle avoidance decision tree | 16 | 32 | Y | Not started
| Program target tracking | 80 | 160 |  | Not started
| Program simultaneous target tracking and obstacle avoidance with interrupt-based state machine architecture | 80 | 160 |  | Not started
| Time Required (All Tasks) | 264 | 528
| Time Required (Fall 2018 Tasks) | 99 | 198
16

## Gantt Chart
Week
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Phase | Mechanical Design | bar: Week 1 to Week 4
Analysis | bar: Week 2 to Week 3
Part Selection | bar: Week 2 to Week 6
Prototyping | bar: Week 4 to Week 9
Testing/Tuning | bar: Week 7 to Week 15
Controls | bar: Week 3; Week 6 to Week 7; Week 10 to Week 14
Target Milestones
End of:
|  | Week 4 | CAD assembly completed. After this point, only tweaks and modifications should be necessary.
|  | Week 6 | Electrical wiring/soldering/connectorizing should be complete.
|  | Week 7 | Basic motor control functions should be complete and sensors should be individually function-checked.
|  | Week 14 | Obstacle avoidance should be demonstrable and logical.
|  | Week 15 | Prototype demonstration/presentation.

## BOM
Part | Unit Price | Quantity | Price | Source | Purpose
Arduino Mega | 36.47 | 1 | 36.47 | Amazon | Controls
Ultrasonic sensor | 1.956 | 5 | 9.78 | Amazon | Controls
Plywood/acrylic sheet | 50 | All | 50 | Maker Studio | Electronics enclosure; basket
Wheel | 15 | 2 | 30 | Amazon | Wheel base
Spherical caster | 15 | 1 | 15 | Amazon | Wheel base
Encoder DC motor | 25 | 2 | 50 | Amazon | Power distribution; controls
180 degree servomotor | 10 | 1 | 10 | Amazon | Controls
Wood studs | 50 | All | 50 | Home Depot | Mechanical frame
Wood screws | 12 | Pack | 12 | Amazon | Mechanical joining
Metric fasteners (M2.5/M3) | 17 | Pack | 17 | Amazon | Electronics mounting
|  | Total: | 280.25